Project Schedule

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Schedule | Start Date | End Date | Estimate Days | Responsible |
| Initiating Tasks | | | | |
| Selecting Project Leader | Thu, 18/2/2021 | Thu, 18/2/2021 | 1 day | All |
| Conducting Research | Fri, 19/2/2021 | Mon, 22/2/2021 | 3 days | All |
| Identifying Project Background | Tue, 23/2/2021 | Wed, 24/2/2021 | 2 days | All |
| Identifying Project Aims and Objectives | Thu, 25/2/2021 | Thu, 25/2/2021 | 1 day | All |
| Identifying Functional and Non-functional Requirements | Fri, 26/2/2021 | Mon, 1/3/2021 | 3 days | All |
| Finishing Project Initiation + | Wed, 3/3/2021 | Wed, 3/3/2021 | 0 day | All |
| Planning Tasks | | | | |
| Determining Project Scope | Fri, 19/2/2021 | Sat, 20/2/2021 | 2 days | All |
| Establishing WBS | Sat, 20/2/2021 | Sat, 20/2/2021 | 1 day | Siva |
| Milestones/Deliverable | Sat, 20/2/2021 | Sat, 20/2/2021 | 1 day | Siva |
| Project Schedule and Baseline Gantt Chart | Sat, 20/2/2021 | Sat, 20/2/2021 | 1 day | Wulan |
| Development and Demonstration Platform | Mon, 22/2/2021 | Tue, 23/2/2021 | 2 days | Awidya |
| Risk Management Plan | Wed, 24/2/2021 | Thu 25/2/2021 | 2 days | Siva |
| Modelling Use Case Diagram and Class Diagram | Fri, 26/2/2021 | Mon, 1/3/2021 | 3 days | Siva |
| Expanded Use Cases and System Sequence Diagrams | Tue, 2/3/2021 | Thu, 4/3/2021 | 3 days | Awidya |
| Analysis Class Diagram | Fri, 5/3/2021 | Sat, 6/3/2021 | 2 days | All |
| Executing Tasks | | | | |
| Designing the Web Page | Mon, 8/3/2021 | Tue, 6/4/2021 | 25 days | All |
| Developing Prototype | Mon, 8/3/2021 | Tue, 6/4/2021 | 26 days | All |
| System Finishing | Wed, 7/4/2021 | Wed, 21/4/2021 | 13 days | All |
| Monitoring and Controlling Tasks | | | | |
| Updating Gantt Chart | Mon, 22/2/2021 | Fri, 30/4/2021 | 58 days | All |
| Testing the Prototype + | Wed, 7/4/2021 | Thu 8/4/2021 | 2 days | All |
| Testing the Complete System + | Fri, 23/4/2021 | Fri, 23/4/2021 | 3 days | All |
| Closing | | | | |
| Final Report + | Wed, 28/4/2021 | Wed, 28/4/2021 | 3 days | All |